## Action_Items
https://kb.epam.com/spaces/GDOKB/pages/1251409344/Data+Science+Projects+-+India
| Owner | Sttaus
If the columns in the confluence page are sufficient enough |  | Completed
Location to store case studies | Anirban | Completed
How to automate the process in cloud
Algorithm list for new GenAI tools and framework
worlflow diagram for the entire process
Code improvement
add date column before use case. Look at project start for format | Kaushik
create the draft for communicating with RM's for confluence page fillup | Kaushik

## Sheet1
| Steps | Tasks | Owner | Start Date | End Date | Status | File/Folder location | Comment
1 | Linking KB page to Python notebook | explore linking between Python notebook and KB page - request/beautiful soup | Gnana | 2025-06-17 |  |  | Data Science Projects - India - GDO Public KB - EPAM Knowledge Base
2 | Data analysis and output preparation | Input data structure for visuals | Kalpesh
|  | Explore current notebook and input file | Anirban
3 | Python notebook output staging - SQL lite | Explore linking between python and teams folder | Anirban | 2025-06-17 | 2025-06-19 | completed |  | We will ignore it for now as there is no direct way
4 | Data storage to PowerBI linking | One drive | Gnana |  |  |  |  | Option 1: teams folder excel file Option 2: create a small DB in cloud
|  | Azure blob | Anirban
5 | PowerBI screens building | Explore feasibility of current screen | Kalpesh | 2025-06-17 | 2025-06-19 | completed
|  | Power Bi pro license - workspace access | Anirban | 2025-06-19 | 2025-06-20 |  |  | we will go ahead with desktop version
|  | Compliance for accessing KB page | Anirban | 2025-06-19 | 2025-06-20 |  |  | Programmatic Access to KB - EPAM.AI Program - EPAM Knowledge Base
|  | Data cleaning | Kalpesh: 5,6,7,8,9 Gnana: 12,13,14,15,16 Anirban:

## Sheet2
Column 1 | Client Name |  | Column 1 | Client Name
Column 2 | Count of Projects |  | Column 2 | Status
|  |  | Column 3 | Count of Projects
Column 1 | Algorithm Segment Level 1
Column 2 | Algorithm Segment Level 2
Column 3 | Count of Projects
|  | Column 1 | Core Technology
|  | Column 2 | No. of Projects